## Environment_ServerSystem_List (hidden)
SystemName | Component | Framework | Language | Platform Runtime | Remark | DevOps Env. Server | UAT Env. Server | PROD Env. Server | OSType
D-Connect | Web App D-Connect Frontend | React | JavaScript | IIS WebServer | ⯈ Login Web: https://khpentest.dai-ichi-life.com.vn/ Mã KH: 0002375090 Mật khẩu: 123456789 ⯈ RemoteDesktop to Server: IP: 10.166.2.55 Username: Administrator Password: P@ssw0rd SA PIC1: Tuong, Nguyen Phuc Kien [Tech/IT SA] SA PIC2: Phong, Nguyen Hoai [Tech/IT OPs & Client Services] ⯈ E:\d-connect-web\build | https://khpentest.dai-ichi-life.com.vn/ 10.166.2.55 | https://khuat.dai-ichi-life.com.vn/ 10.166.2.37 | https://kh.dai-ichi-life.com.vn/ 10.166.0.14, 10.166.0.69 | Windows
| API D-Connect Backend Service | Spring Boot | Java | JVM | Start .jar file with port 8080 ⯈ E:\d-connect | 10.166.2.55 | 10.166.2.37 | 10.166.0.14, 10.166.0.69 | Windows | Promote Guide xin SA
| API D-Connect Parner (irace, aktivolabs) | Spring Boot | Java | JVM | Start .jar file with port 8081 ⯈ E:\dc-partner | 10.166.2.55 | 10.166.2.37 | 10.166.0.14, 10.166.0.69 | Windows
| Database cportal |  |  | MSSQL 2022 | jdbc:sqlserver://dbuat_cportal.dai-ichi-life.com.vn:1433;databaseName=Cportal | 10.166.2.157 | 10.166.2.157 ansible_user / QmYWv2v9cfgZUb3YceLE | 10.166.1.30 | Windows
| Database centdb |  |  | MSSQL 2022 | jdbc:sqlserver://dbuat_centdb.dai-ichi-life.com.vn:1433;databaseName=CentDB | 10.166.2.157 | 10.166.2.157 ansible_user / QmYWv2v9cfgZUb3YceLE | 10.166.1.30 | Windows
| Database mCP |  |  | MSSQL 2022 | jdbc:sqlserver://10.166.2.157:1433;databaseName=mCP | 10.166.2.157 | 10.166.2.157 ansible_user / QmYWv2v9cfgZUb3YceLE | 10.166.1.45 | Windows
| Database ODS |  |  | DB2 11.5 | jdbc:db2://10.166.2.154:50000/ODSUAT02 | 10.166.2.154/ODSUAT02 | 10.166.2.154/ODSUAT02 | 10.166.0.190/ODSPRD | IBM Linux Power
| eDoctor - Tư vấn sức khỏe | npm/Node.js | JavaScript | Node.js | Source của đối tác deploy trên server DLVN |  |  | 10.166.0.14, 10.166.0.69 | Windows
| API of IBM ACE (iib-cp-ace-uat-ir) | IBM ACE | Java | Containers
D-Success | Web App D-Success for User | React | JavaScript | Apache/2.4.53 httpd | /var/www/html stop/start httpd service (# systemctl restart httpd) | 10.166.2.237 | https://dsuccessuat.dai-ichi-life.com.vn/ 10.166.2.21 |  | Linux
| Web App D-Success for Admin | Spring Boot | Java | JBoss EAP 7.3 | /opt/jboss/jboss-eap-7.3/standalone/deployments/admin.war | 10.166.2.237 | http://10.166.2.22:8080/admin/ 10.166.2.22 |  | Linux
| API D-Success | Spring Boot | Java | JBoss EAP 7.3 | /opt/jboss/jboss-eap-7.3/standalone/deployments/api.war | 10.166.2.237 | 10.166.2.22 |  | Linux
| eApp for D-Success | React | JavaScript | IIS WebServer | eapp4ds |  | 10.166.2.118 |  | Windows
| eCV for D-Success | React | JavaScript | IIS WebServer | ecv4ds erecuirment |  | 10.166.2.118 |  | Windows
| Database dsuccess |  |  | MSSQL 2022 | jdbc:sqlserver://dbuat_dsuccess.dai-ichi-life.com.vn:1433;databaseName=dsuccessuat |  | 10.166.2.232
| Database ODS |  |  | DB2 11.5 | jdbc:db2://dbuat_ods.dai-ichi-life.com.vn:50000/ODSUAT02 |  | 10.166.2.154/ODSUAT02
| API of IBM ACE (iib-mobile-ace-uat-ir) | IBM ACE | Java | Containers
| Web App ADPortal *Backend API dùng chung D-Success | React | JavaScript | Apache/2.4.53 httpd | /var/www/html stop/start httpd service (# systemctl restart httpd) |  | https://ad-portaluat.dai-ichi-life.com.vn/ 10.166.2.67 |  | Linux
GitLab | [5 empty] | https://gitlabtest.dai-ichi-life.com.vn/ | 10.166.2.118 | https://git.dai-ichi-life.com.vn/ | Linux
GitLab Runner |  |  |  |  | Thực hiện quá trình build source code, package được trigger từ GitLab CI | 10.166.2.18 | 10.166.4.27 | 10.166.4.27 | Linux
Harbor Registry |  |  |  |  | Lưu trữ image container trong quá trình CI/CD | https://registry.dai-ichi-life.com.vn/ | https://registry.dai-ichi-life.com.vn/ | https://registry.dai-ichi-life.com.vn/ | Linux
RedHat OpenShift (OCP) + ArgoCD | [5 empty] | https://oauth-openshift.apps.oscldev.dai-ichi-life.com.vn/ | https://console-openshift-console.apps.osclsit.dai-ichi-life.com.vn/ | https://console-openshift-console.apps.osclibmprd.dai-ichi-life.com.vn/ | Linux
RedHat Ansible (AAP) |  |  |  |  | admin/Ansible@12345$ | https://hoslabdevopsasb.dai-ichi-life.com.vn/ 10.166.2.28 | 10.166.2.74 | 10.166.0.123 | Linux
Elastic Search (ELK) | [5 empty] | https://elkace.dai-ichi-life.com.vn/ | https://elkace.dai-ichi-life.com.vn/ | https://elkace.dai-ichi-life.com.vn/

## RACI
[8 empty] | R | A | C | I
No. | Stage | Step | Description | Deliverables | Deliverables Components (What) | Rules | Input | Responsible | Accountable | Consulted | Informed
Auto Increase |  | Step Name | What/Why | Output (files, …) | Details Component inside the output | When/How | Input documents that help perform this step | The person who performs the task directly | The person ultimately responsible, who makes decisions and owns the outcome | The person with expertise who is consulted for input | The person who needs to be kept updated on progress and results
No. –––––––– Auto Increase | Stage –––––––– | Step –––––––––– Step Name | Description –––––––––– What/Why | Deliverables –––––––––– Output (files, …) | Deliverables Components (What) –––––––––– Details Component inside the output | Rules –––––––––– When/How | Input –––––––––– Input documents that help perform this step | Responsible –––––––––– The person who performs the task directly | Accountable –––––––––– The person ultimately responsible, who makes decisions and owns the outcome | Consulted –––––––––– The person with expertise who is consulted for input | Informed –––––––––– The person who needs to be kept updated on progress and results | Is Documented | Effort
1 | Preparation | Provide application components | Ensure the CI/CD pipeline accurately replicates the real environment, reducing deployment errors and supporting reliable automated deployments. | DevOps Form |  | Review the Application Inventory document (Components Technology Stack sheet) to list all application components, including web apps, backend services, APIs, databases, and external integrations. | Application Inventory Document | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | Done |  |  | 7 | DevOps Engineering Standards
2 | Preparation | Provide System Architecture |  | Architecture Diagram |  | Create and provide a high-level architecture diagram showing system components, their interactions, and dependencies. | N/A | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | Done |  |  | 16 | DevOps Operation Standards
1 | Preparation | Provide Build Steps |  | Build Form |  | Identify and provide the build steps and commands to compile and package the source code into deployable artifacts (files, Docker images…) when the build is executed. |  | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | Done
2 | Preparation | Provide Deployment Documentation |  | Deployment Form |  | Provide installation/promote documentation for application components | N/A | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | Done
4 | Preparation | Provide Configuration (Local/DEV) | Ensure no config files are missing, prevent runtime errors, and maintain consistent file management across environments. | Configuration Form |  | Identify configuration files for application components in the local or development environment. | N/A | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | Done
5 | Preparation | Provide Configuration (UAT/PRD) |  | Configuration Form |  | Identify configuration files for application components in the UAT or production environment. | N/A | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | Done
x | Preparation | Identify Outbound Connectivity | This step ensures the application’s network requirements are understood, enabling accurate network policy configuration, enhanced security, and reliable operation | Port Opening Request Form |  | Identify required outbound connections (ports, protocols, destinations) to support egress/ingress and network policies. | Architecture Diagram | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | Done
3 | Preparation | Provide Operation Documentation | Ensure the CI/CD pipeline accurately replicates the real environment, reducing deployment errors and supporting reliable automated deployments. | Operation Form |  | Provide operation documentation for application components | N/A | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | Done
6 | Preparation | Verify and Align Configuration Files Across Environments |  | Updated Configuration Form |  | Confirm with both the local DEV and UAT SA to ensure the file locations are consistent, as files may be stored differently between local and UAT environments. | Configuration Form | System Architecture | Squad Leader, Technical Leader | Developer | System Administrator | To Do | 0.5
7 | Preparation | Manage Application Configuration | Allows flexible config management across environments without rebuilding the app and ensures correct mounting in CI/CD deployments. | Updated Source Code |  | Move configuration files out of the packaged application (WAR/JAR) so that the application reads them from an external source—either an external path via environment variables defined in the Helm Chart or from a dedicated Application Configuration repository on GitLab storing the variables (for Ansible Playbook use cases). | N/A | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | To Do | 1
8 | Preparation | Identify Filesystem & Storage | Ensure correct access and permissions for shared storage, replicate filesystem behavior in OpenShift, and prevent runtime errors due to missing or inaccessible folders. | File Path List, Permissions List |  | Identify direct filesystem usage (Qumulo) and determine the need for persistent storage mapping (PVC) | N/A | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | To Do | 2
9 | Preparation | Configure Path Mapping | Ensures the app reads/writes files correctly in production containers, handling dev vs. converted vs. relative paths consistently. | Updated Source Code |  | Implement path conversion using FileServerUtil with feature flags (pathInDatabaseMode) to map shared folder paths from network drives to container mount paths at runtime. | mounted path, app path | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | To Do | 2
10 | Preparation | Review Scheduled Jobs | Ensures scheduled jobs run independently from the main application, enabling flexible deployment and easier management on OpenShift. | Updated Source Code |  | Review scheduled tasks and modify the app to add a config flag (in .config file or environment variable) to enable/disable scheduled jobs, allowing separate deployments for the app and for jobs via Helm Chart. | N/A | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | To Do | 2
11 | Preparation | Switch Application Logging to Console | Allows a logging agent (OpenShift) to collect pod logs automatically and forward them to centralized logging system (ELK), ensuring centralized log management for CI/CD environments. | Updated Source Code |  | Configure the app to log to console instead of files so a logging agent can collect logs from pods and send them to a centralized logging system. | N/A | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | To Do | 2
12 | Preparation | Create application configuration override repository | Provides a centralized, environment-specific place to store configuration overrides, making management and versioning easier. | Repositories in ManagementConfig group in GitLab, configuration files |  | Create repositories for each environment following DevOps Operation Standards document | N/A | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | Done | 2 | DevOps Operation Standards
13 | Preparation | Init application configuration override | Establishes the baseline configuration for each environment, ensuring CI/CD pipelines have the correct environment settings. | Application Configuration Files |  | Create configuration files for each environment in the repository. | N/A | System Architecture | Squad Leader, Technical Leader | Developer | System Administrator | Done
14 | Preparation | Update application configuration override | Keeps environment-specific settings up to date at all times, ensuring deployments always run with the correct configuration. | Application Configuration Files |  | Update configuration files for each environment in the repository. | N/A | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | Done
15 | CI | Build Application Aritifacts | Provides a clear, consistent, and reproducible build process that serves as the foundation for CI/CD deployments, whether deploying containers on OpenShift or artifacts on On-Prem via Ansible. | Dockerfile |  | Define and implement the build steps for the application, including creating Dockerfile for containerized deployment or commands/scripts for On-Prem deployment. Follow best practices, configure base environment, manage shared folders/configs, and ensure steps are testable and reproducible. | N/A | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | Done | 2
16 | CI | Add CI Pipeline Definition File | Enable automated and consistent CI execution. | .gitlab-ci.yml |  | Configure GitLab CI Pipeline for application component repository | Base CI pipeline | Developer | Squad Leader, Technical Leader | System Architecture | System Administrator | Done
17 | CI | Create GitLab Group Access Token | Enables CI/CD pipelines to securely push updates to the Helm Chart repo without | Group Access Token (Token Name, Group Access Token Value) |  | Create Group Access Token for update build version to Helm Chart Repository | Variable Name | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | Done
18 | CI | Manage Artifact Registry Projects & Permissions | Ensure the CI/CD pipeline can securely store and access images, keep naming consistent with Git, and maintain clear permissions. | Harbor projects, Permissions |  | Create a Harbor project following the Git Subgroup Slug convention (e.g., d-connect-system/d-connect-backend). Assign pull/push permissions to accounts: - CI account: pull base images and push application images. - OpenShift account: pull application images for deployment. DevOps Operation Standards document | Slug name of GitLab repositories of application components | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | Done | 0.5 | DevOps Operation Standards
19 | CI | Configure GitLab CI Runner & Variables | Enable automated and secure CI execution. | GitLab Runner set up on server Repository variables configured |  | Set up GitLab CI by creating a Runner on the server and configuring repository variables ([Guideline]_Gitlab_Project_Setup_and_Role_Base_Access_Control.pdf) | Access to GitLab repository, server credentials | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | Done | 2
20 | CI | Update CI Base Pipeline | Maintain consistency, enable reuse, and support flexible project-specific needs. | Updated CI base pipeline |  | Modify the CI base pipeline when the existing base template does not meet project requirements. Copy from an existing base pipeline and keep the standard structure. Follow common build practices and maintain guidelines ( DevOps Engineering Standards document) | N/A | System Architecture | Squad Leader, Technical Leader | System Architecture | Developer | Done | 2 | DevOps Engineering Standards
21 | CD On Cloud | Configure Deployment Namespace & Access Management | Ensure traceability, and secure deployment management. | OpenShift namesapce, RBAC |  | Create OpenShift namespace and RBAC following DevOps Operation Standards document | Name of GitLab repositories of application components | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Operation Standards
22 | CD On Cloud | Configure Image Pull Secrets | Enable secure image pulls from the private registry. | Secrets for pull images |  | Annual Configure image pull secrets on OpenShift, GitLab Variables (Global Admin Area) following DevOps Operation Standards document | Token Name, Group Access Token Value | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Operation Standards
23 | CD On Cloud | Create Helm Chart repositories | Ensure version-controlled Helm charts for automated OpenShift deployments with correct configuration and persistent data. | GitOps/UAT/HelmChart Repository GitOps/PRD/HelmChart Repository |  | Follow pattern name HelmChart<GitLabSystemGroupName><Environment> following DevOps Operation Standards document | GitLab System Group Name | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Operation Standards
24 | CD On Cloud | Develop Helm Chart | Enable standardized and automated deployments. | Created Helm Chart |  | Develop Helm charts following the DevOps Engineering Standards document | All deliverables of Step 1 to Step 10 | System Architecture | Squad Leader, Technical Leader | Developer | System Administrator | To Do | 2 | DevOps Engineering Standards
25 | CD On Cloud | Update Helm Chart | Keep deployments accurate and up to date. | Updated Helm Chart |  | Update Helm Charts |  | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Engineering Standards
26 | CD On Cloud | Configure Applications & Access in GitOps Controller | To enable controlled and automated deployments to OpenShift while allowing the team to monitor and manage releases securely. | - Argo CD Project created - Argo CD Application created - Helm chart & values configured - Sync policy configured - LDAP access roles assigned |  | Create the Argo CD project and application, configure the Helm chart and environment-specific values, and assign access permissions following the DevOps Operation Standards document | Helm Repositories in GitLab | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Operation Standards
27 | CD On Cloud | Configure Traffic Routing | To ensure stable and seamless access to applications, and support failover or parallel routing between on-prem and OpenShift environments. | DataPower or F5 configurations |  | Configure traffic routing using DataPower or F5 to map domains, IPs, and ports to OpenShift services and enable load balancing following the DevOps Operation Standards document | Name of GitLab repositories of application components | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 2 | DevOps Operation Standards
28 | CD On Premise | Define On-Prem Deployment as Code | To codify the deployment process as automation so releases can be executed consistently and safely across environments, minimizing manual steps and enabling reliable Continuous Deployment. | Ansible playbook YAML file |  | Define deployment automation for On-Prem environments by creating deployment manifests and scripts (currently implemented using Ansible playbooks) to standardize application rollout across servers. Following DevOps Engineering Standards document | Build steps | System Architecture | Squad Leader, Technical Leader | Developer | System Administrator | To Do | 2 | DevOps Engineering Standards
29 | CD On Premise | Prepare Server Access Account | Allow Ansible to securely connect and execute deployment operations without using personal or root accounts. | - Server Access Account - Proper permissions (SSH access, sudo if required, file/service control) |  | Create a dedicated remote user account on target servers for deployment automation and grant required permissions for application deployment tasks. Following DevOps Operation Standards document | Target Server | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 2 | DevOps Operation Standards
30 | CD On Premise | Define Authentication Method | Standardize how authentication information is structured and securely managed, enabling reusable and consistent credential configuration across projects. | Credential Type configured in Ansible Defined authentication fields (username/password/SSH key/etc.) |  | Define or select the appropriate credential type in Ansible (e.g., Machine/SSH, Source Control, or custom type) to specify the authentication schema required for remote connections. Following DevOps Operation Standards document | Authentication Schema | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Operation Standards
31 | CD On Premise | Configure Deployment Credentials | Enable secure and centralized credential management for automated deployments. | Credential entry in Ansible |  | Register the server access credentials (username/password or SSH key) in Ansible to authenticate remote connections. Following DevOps Operation Standards document | Server Access Acount | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Operation Standards
32 | CD On Premise | Register Target Hosts | Allow Ansible to know where deployments should be executed. | Hosts or inventory groups configured in Ansible |  | Add target servers (hostname/IP/port/credential) into Ansible inventory for deployment targeting. Following DevOps Operation Standards document | Hostname, IP, Port, Credential | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Operation Standards
33 | CD On Premise | Register Deployment Project Repository | Allow Ansible to fetch and version-control deployment automation scripts. | Ansible Project connected to Git repo |  | Create an Ansible Project linked to the Git repository containing deployment playbooks. Following DevOps Operation Standards document | GitLab Ansible Playbook Repository | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Operation Standards
34 | CD On Premise | Create Deployment Execution Template | Provide a standardized and repeatable way to trigger deployments. | Job Template Survey inputs (environment/host selection) |  | Create a Job Template that defines inventory, project, playbook, credentials, and runtime variables for executing deployments. Following DevOps Operation Standards document | Inventory, Project, Playbook, Credentials, Runtime Variables | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Operation Standards
35 | CD On Premise | Configure Access Control | Ensure only authorized users can trigger or manage deployments while maintaining auditability. | Teams LDAP users Role assignments (read/execute/admin) |  | Create teams, enable LDAP login, assign users, and grant appropriate roles to access deployment resources Following DevOps Operation Standards document | Agile Team Name LDAP user Job Template | System Administrator | Squad Leader, Technical Leader | System Architecture | Developer | To Do | 1 | DevOps Operation Standards
36
- | - | - | - | - | - | - | - | - | - | - | -
Note on E5: Biết được bao nhiêu môi trường, mỗi môi trường có khác nhau không, để integration testing.
Note on G19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Operation Standards” document - Section GitLab/ApplicationConfiguration - SA in charge
Note on G25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Operation Standards” document - Section Harbor - SA in charge
Note on G26: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần update guideline để hướng dẫn tạo Runner trên Server Linux
Note on G27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Engineering Standards” - Section GitLab Pipeline
Note on G28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Operation Standards” document - Section OpenShift - SA in charge
Note on G29: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Operation Standards” document - Section OpenShift - Section GitLab - SA in charge
Note on G30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Operation Standards” document - Section GitLab/Helm - SA in charge
Note on G31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Engineering Standards” - Section Helm Chart
Note on G32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: SA chỉ update file values? Còn những file templates/chart thì System Architecture? Cần tách rõ ra 2 dòng? Update values in HelmChart? Update templates in HelmChart?
Note on G33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Operation Standards” document - Section Argo CD - SA in charge
Note on G34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Operation Standards” document - Section F5 Load Balancing - SA in charge
Note on G35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Engineering Standards” - Section Ansible Playbook
Note on G36: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cần develop “DevOps Operation Standards” document - Section OpenShift - SA in charge

## CI.CD OpenShift Steps
No. | Mapping Task | Task | PIC | CI/CD Related Files | Category | Output | Action | Example | Link File Example | UAT File Example On Prem | Estimate | Comment | So sánh với On-Prem | Is Documented
1 | Identify application components, architecture of system | Lấy danh sách nhóm ứng dụng và kèm với tài liệu cài đặt/vận hành (cài đặt ban đầu và mỗi khi promote/golive) | SA, DEV | Dockerfile | Collect Information for Dockerfile | 1 file word, file note | Book meeting để SA, DEV mở file word đã có lên trình bày cho System Architecture nắm thông tin và note lại những điểm cần biết: Server nào, IP nào, Runtime Version, Web Server Version, Tech Stack Related Version. Cần những thông tin này để có thông tin làm tương tự trên Docker (giống như dời server đó vào Docker). | Xin anh Tuấn |  | - | - | Hỏi lại anh Tuấn các file note trước đây đã lưu | giống | Done
2 | Identitfy Application Configuration | Lấy danh sách file config của các ứng dụng (file name, location) | SA, DEV | Dockerfile, HELM Chart | Collect Information for Dockerfile CD | File Path, List Config Files | Liên hệ trực tiếp qua tận bàn hỏi, mấy file, nằm ở đâu. Hỏi DEV ở local, hỏi SA ở UAT. Confirm 2 người xem khớp không đủ chưa, đôi khi ở local đặt chỗ đây, ở UAT đặt chỗ khác. Ví dụ Java, file ở local nằm trong source code, trên server UAT on prem thì nằm cùng cấp ở file JAR. Mục tiêu để biết có bao nhiêu file để quản lý trên OpenShift đủ file. Ví dụ khi lên OpenShift sẽ được config trong Helm Chart mountPath: "/home/appconfig" | .env, application.properties, appsettings.config | Local File | Nằm cùng cấp ở file .jar | - | - | giống | Done
3 | Configuration Management | Đưa file config ra ngoài file đóng gói ứng dụng (war,…) | DEV | Application Source Code, HELM Chart, Dockerfile | Update Source Code CD | Source Code Updated | Yêu cầu DEV sửa, đưa config ra ngoài file đóng gói ứng dụng (war), sửa code lại để đừng đọc trong các file config trong source code nữa, mà phải đọc ở ngoài, để có mount file path tới bất kỳ đâu cũng được thông qua biến môi trường, biến môi trường đó sẽ được config trong Helm Chart. | Đọc trong file HELM, Dockerfile | Link file trong comment | - | - | - | giống | Done
4 | Filesystem & Storage | Liệt kê các config đường dẫn folder share (ví dụ Qumulo, share network drive) hoặc đường dẫn folder không share như window server temp folder ổ vật lý (server run chính application): + Lưu config ở đâu? + Có đọc/ghi file? | DEV | HELM Chart (YAML) | Collect Information for Helm Chart CD on OpenShift | List File Path, Quyền | Hỏi ứng dụng đó có ghi vào Qumulo không? Để xin cấp quyền ghi (ví dụ trường hợp 1 thằng ghi nhưng mà có 10 thằng đọc). Phục vụ cho việc cấp quyền khi lên OpenShift. Cấp quyền ở nhiều nơi (Qumulo, OpenShift) giúp chặn nhiều tầng. PV/PVC: volumes, volumeMounts trong Helm Chart (tương tự như tính chất share folder của onedrive, nhiều người share thì config nhiều volume, volumeMounts) Volumemount name: server trên container nào Volumemount path: đường dẫn nào (Qumulo sẽ mapping hình ảnh dữ liệu vào folder này, container sẽ đọc để lấy dữ liệu) | Đọc trong file HELM | https://git.dai-ichi-life.com.vn/gitops/uat/helm-chart-d-connect-system-uat/-/blob/main/d-connect-backend/values.uat.yaml?ref_type=heads | - | - | - | On-Prem không có bước này | Done
5 | Path mapping | Dùng class FileServerUtil để convert những đường dẫn folder share trên, trước khi đọc ghi files. | DEV |  | Update Source Code CD on OpenShift | Source Code Updated | Implement feature flags pathInDatabaseMode, để convert đường dẫn khi runtime trên production. Có 4 giá trị: 0,1,2,3 (0: dev - no convert , 1: convert from database, 2: đã convert rồi, 3: lưu đường dẫn tương đối chỉ folder-name) Trước: đường dẫn network drive, ví dụ: //ip:port/folder-name Sau: /mnt/folder-name (mnt: mount) |  |  | - | - | - |  | Done
6 | Scheduled Jobs | Tách, quản lý cron job/ scheduler ra chạy độc lập | DEV | Application Source Code, HELM Chart | Update Source Code CD on OpenShift | Source Code Updated | Yêu cầu dev enhance thêm cờ config (ví dụ thêm cờ trong file .config hoặc biến môi trường) để nó chạy hoặc không chạy để khi deploy trên OpenShift sẽ tách ra thành 2 deployment (2 Helm Chart), 1 deployment chỉ chạy ứng dụng, 1 deployment chỉ chạy job. Tạo tiền đề để thêm config vào HELM Chart. | Merge Request D-Connect Backend |  | - | - | - | On-Prem không có bước này | Done
7 | Build Application Container | Cung cấp các bước để build | DEV | Dockerfile | CI | Build Steps | Thông thường là 1 lệnh command line | [6 empty] | To Do
8 | Build Application Container | Chuyển đổi thành containerized app (run with Dockerfile): + Tạo/search base image. + Mount thư mục share (qmulo,...), config, log. + File .dockerignore. Run docker chạy thử nghiệm | DEV | Dockerfile | CI |  | o Chạy non-root user - root user quyền cao, dễ rò rỉ bảo mật o Khai báo WORKDIR rõ ràng - luôn khai báo WORKDIR, tránh quên khai báo nó sẽ lấy defautl (đây là 1 best practice), lí do thì google thêm (ví dụ giúp copy đúng workdir) o COPY đúng artifact cần thiết - tránh copy cái không xài (như runtime), ví dụ chỉ cần copy file build thì copy file build thôi. o Không hardcode cấu hình - không hard code, dùng qua 1 biến ENV, có thể linh động thay đổi giá trị thông qua config trên HELM chart. o Không embed secret - config trong HELM chart o Không expose port dư thừa - ra 1 port thôi, dư thừa khó quản lý, bảo mật thấp, liên quan tới mạng network - Không Custom OS package không cần thiết cho runtime - ví dụ Server chỉ cần cài JVM là đủ mà cài thêm Python dư (thường gặp lỗi này là do copy paste dockerfile trên mạng mà không hiểu bị dư) Chạy thử nghiệm với lệnh Docker Run, truyền giá trị của các ENV vào lệnh (tương tự như HELM Chart trên OpenShift) |  |  | - | 2-3 days | - | On-Prem không có bước này | Done
9 | Switch Application Logging to Console | Chuyển ghi log ra file thành log console nếu chạy trên k8s (OpenShift) | DEV | Application Source Code, Helm chart (YAML) | Configure File Logging to Console Log CD on OpenShift | Source Code Updated | Sửa file config của library ghi log (ví dụ Log4j.xml) (chi tiết cách sửa trên trang chủ của thư viện hướng dẫn, lưu ý tùy theo version sẽ có sự khác nhau) <appender name="Console" <root level="info"> <appender-ref ref="RollingFile" /> <appender-ref ref="Console" /> </root> Khi đã ghi console log thì sẽ có 1 con agent của OpenShift quét Console các Pod đẩy qua ELK (việc config đẩy qua ELK đã được làm khi SA dựng OpenShift lên rồi). | logback-spring.xml | https://git.dai-ichi-life.com.vn/dlvn/d-connect-system/d-connect-backend/-/blob/main/src/main/resources/logback-spring.xml?ref_type=heads | - | - | - |  | Done
10 | Create Helm Charts repositories | Tạo project gitops (dùng helm chart): đưa app config vào ConfigMap, Secret; mount folder report to PV | System Architecture init file, SA update nếu có | Helm chart (YAML) | CD on OpenShift |  | Tạo project HelmChart theo Subgroup System - Pattern Name: HelmChart<SubGroupName><Uat/Prd> - Tạo folder theo project-slug - Tạo cấu trúc bên trong folder theo chuẩn Helm Charts: + builds + templates + .helmignore + Chart.yaml + values.uat-scheduler.yaml (optional tùy theo project) + values.uat.yaml + values.yaml (file gốc) Develop Helm builds: - tạo file <project-slug>-<env (uat/uat1/prd>.buildversion templates: có 2 nhóm chính: ACE và khác ACE - templates khác ACE, gồm các files như hình bên cạnh (giữ nguyên hoặc custom khi có nhu cầu) - .helmignore; giữ nguyên - Chart.yaml: chỉ sửa name - values.uat.yaml / values.yaml / values.uat-scheduler.yaml: copy mẫu, xóa những key không cần thiết, giữ những key cần. Cơ chế của Helm là: - file values.yaml là file gốc chứa all key và default value - files values.env(uat/uat-scheduler, uat1,...) sẽ ghi đè những giá trị của file value này lên file gốc Thứ tự định nghĩa trong lúc tạo app trên ArgoCD sẽ là dạng chọn multiple value dropdownlist: - values.yaml, values.uat.yaml Như vậy Argo sẽ hiểu là nạp values.yaml trước sau đó ghi đè values.uat (từ trái sang phải) | #VALUE! | https://git.dai-ichi-life.com.vn/gitops/uat/helm-chart-d-connect-system-uat/-/tree/main/d-connect-backend?ref_type=heads | - | 2 days | - |  | Done
11 | GitLab CI Pipeline | Tạo file .gitlab-ci.yml để chạy pipeline. | System Architecture | .gitlab-ci.yml | CI |  | Viết .gilab-ci.yml trong từng project cần thực hiện CI (copy file mẫu từ project khác nếu đã làm rồi). Trường hợp chưa có file mẫu, cần viết base pipeline mới ở bước base pipeline bên dưới. |  | https://git.dai-ichi-life.com.vn/dlvn/d-connect-system/d-connect-backend/-/blob/main/.gitlab-ci.yml?ref_type=heads | - | 1-2 days | - |  | Done
12 | Configure GitLab CI | Cấu hình Gitlab CI: + Settings -> CICD -> Runners (tạo Runner trên Server và settings) + Settings -> CICD -> Variables. | System Administrator | .gitlab-ci.yml | CI |  | Tạo Runner trên server bằng commandline Configure Runner, Variables trên GitLab repository. |  |  | - | - | - |  | Done
13 | CI base pipeline | Sửa CI base pipeline trong trường hợp base không đáp ứng được |  |  |  |  | Có 2 dạng base: base theo framework, base chung cho tất cả framework. pipeline-maven/maven-openshift.gitlab-ci.yml base.gitlab-ci.yml - đề xuất CODEOWNER của file là anh Trực. Copy từ một base pipeline hiện có, giữ nguyên cấu trúc (includes, stages, validation, prepare-build, build, update-buildversion, deploy), chỉ thay đổi các stages: - prepare-build - build - có phần ghi đè giá trị biến môi trường (ApplicationConfig) - xem lại hiểu những điểm chung cần làm trong stage build để viết guideline Lưu ý: cấu trúc chuẩn có thể thay đổi trong tương lai (bổ sung các stage: scan code, unit test, ....) |  | https://git.dai-ichi-life.com.vn/gitops/pipeline/gitlab-pipeline/-/blob/main/pipeline-maven/maven-openshift.gitlab-ci.yml?ref_type=heads | - | - | - |  | Done
14 | Manage Harbor Projects & Permissions | Config global harbor integration settings admin area | System Architecture |  | CI |  | Đã làm một lần và duy nhất rồi HARBOR_HOST, HARBOR_USERNAME, HARBOR_PASSWORD Không bao giờ hết hạn |  | https://gitlabtest.dai-ichi-life.com.vn/admin/application_settings/integrations | - | - | - |  | Done
15 | Harbor Management | Tạo project và phân quyền trên Harbor | SA |  | CI on OpenShift |  | Đặt name theo Subgroup Slug Git theo kebap-case, ví dụ: d-connect-system/d-connect-backend Phân quyền: cho các tài khoản harbor pull/push (anh Tuấn làm, nhờ anh Tuấn share thêm) - ví dụ CI có 1 tài khoản cho CI pull /push để pull base images push app images, OpenShift có 1 tài khoản - pull app image về để deploy | Nhờ anh Tuấn hoặc SA mở cho coi tử | registry.dai-ichi-life.com.vn/d-connect-system/d-connect-backend | - | - | - |  | Done
16 | OpenShift Namespace & Access Management | Tạo namespace và phân quyền trên OpenShift (namespace trong thuật ngữ của K8S, project trong thuật ngữ OpenShift) | SA |  | CD on OpenShift |  | Đặt name theo Subgroup Slug Git theo kebap-case, ví dụ: d-connect-system/d-connect-backend-uat và thêm suffix môi trường "-dev" hoặc "-uat" (không có chuyện uat1,uat2, tức là các uat1,uat2 đều nằm trong namepsace "-uat" hết) Phân quyền account ldap để vô read (đọc xem có deploy được hông, hoặc lỗi) có thể có quyền khác |  | https://console-openshift-console.apps.oscldev.dai-ichi-life.com.vn/k8s/cluster/project.openshift.io~v1~Project | - | - | - |  | Done
17 | Image Pull Secrets Configuration | Config secret để pull image trên OpenShift cho namespace ở bước trên | SA |  | CD on OpenShift |  | Tạo secret chứa username/token của Harbor |  | https://console-openshift-console.apps.oscldev.dai-ichi-life.com.vn/k8s/all-namespaces/core~v1~Secret | - | - | - |  | Done
18 | Prepare environment-specific configuration | Tạo các file config trên Git ManagementConfig/UAT/ApplicationConfig | System Architecture init file, SA update nếu có |  | CD on On-Prem CI OpenShift(node.js) |  | Trường hợp On-Prem - tất cả file config đều nằm trong các repo này Đối với cả OpenShift và On-Prem - Nodejs, thì các config sẽ được lưu khi build F.Y.I: Trường hợp OpenShift: - tất cả file config đều nằm trong Helm Chart (on-prem có tên file như thế nào thì trong helm chart sẽ có object tên file tương tự, ví dụ: application.properties) - ưu tiên tên chuẩn (có 1 số trường hợp tên file config trong source code không chuẩn ví dụ logback.xml or logback-spring.xml | .env nodejs | https://git.dai-ichi-life.com.vn/management-config/uat/application-config/ad-portal-frontend-config/-/blob/main/build-nodejs/.env.uat?ref_type=heads https://git.dai-ichi-life.com.vn/management-config/uat/application-config/d-connect-backend-config/-/blob/main/deploy-jvm/application.properties.uat?ref_type=heads https://git.dai-ichi-life.com.vn/gitops/uat/helm-chart-d-connect-system-uat/-/blob/main/d-connect-backend/values.uat.yaml?ref_type=heads | - | - | - |  | Done
19 | Argo CD Application & Access Management | Tạo project và application Argo CD và phân quyền | SA |  | CD on OpenShift |  | Chạy HelmChart gì, file value nào (ví dụ HelmChartDConnect, file value uat thì lấy file value.uat.yaml) Phân quyền account ldap để vô read/sync (đọc xem có deploy được hông, hoặc lỗi) có thể có quyền khác, hiện tại technical leader/hoặc đại diện Senior Dev |  |  | - | - | - |  | Done
20 | Traffic Routing Confiugration | Tạo DataPower (cho ACE OpenShift) hoặc tạo/config F5 (các ứng dụng còn lại không phải cho ACE) | SA |  | Route CD on OpenShift |  | Config routing domain/ip/network/port để khi truy cập domain nó sẽ điều hướng tới container của OpenShift. |  |  | - | - | - |  | Done
21 | - | - | - | - | - | - | - | - | - | - | - | - | - | -
22 |  | Tạo folder cho dự án trong repo AnsiblePlaybookUAT và các file manifest (yaml) để chạy trên Ansible | System Architecture |  | CD On-Prem |  | Tạo 1 file manifest theo pattern <project-slug-name>-on-premise-playbook.yaml Copy 1 file template đã có sẵn theo từng loại: - frontend - dotnet - java spring Mỗi file có những cấu trúc sau: name host vars tasks: - Task râu ria (ví dụ: Settings, backup-folder, tùy biến theo từng project) - Task chính Deploy gồm các task nhỏ: - Oras Pull Artifacts - Git Clone Application Configuration - Những bước deploy thực tế tùy dự án khác nhau, ví dụ copy hiện tại, Backup hiện tại, Stop Server, Delete cái hiện tại, Copy mới ghi đè vô, Start, Verify (xem no đã start chưa) - Post tasks (Logout ORAS, Delete temp folder, Retention (xóa những bản backup cũ và giữ 5 cái gần nhất)
| Define On-Prem Deployment as Code | Set up user trên server cần deploy, để lấy user đó config trên Ansible | SA (hiện tại là anh Tuấn) |  | CD On-Prem |  | Ví dụ sử dụng laptop cũng cần user để login, tương tự Ansible cũng cần 1 remote user để login vào server (host) Cụ thể bước làm anh Trực không biết hỏi anh Tuấn (vào Linux Server tạo user rồi cấp quyền cho nó) --> liệt kê kỹ lại các quyền vì đã từng có các trường hợp thiếu quyền.
1 | Define Credential Type | Set up credential type trên Ansible | SA (hiện tại là anh Tuấn) |  | CD On-Prem
2 | Configure Ansible Credentials | Set up credentials trên Ansible | SA (hiện tại là anh Tuấn) |  | CD On-Prem |  | Tạo username/password của user vừa tạo ở bước trên vào danh sách credentials trên Ansible để Ansible sử dụng account này remote login vào server.
3 |  | Set up host trên Ansible | SA (hiện tại là anh Tuấn) |  | CD On-Prem |  | Tạo host (hostname/ip address/port/credentials đã tạo ở trên) trong danh sách host trên Ansible để Ansible sử dụng để kết nối vào server cần deploy.
|  | Tạo project trên Ansible | SA (hiện tại là anh Tuấn) |  | CD On-Prem |  | Tương ứng 1 Git Playbook sẽ có 1 Project - Project này sẽ đọc Git Playbook
|  | Tạo template (JobTemplate) trên Ansible | SA (hiện tại UAT anh Trực, PRD là anh Tuấn) |  | CD On-Prem |  | Trong template đó sẽ bao gồm: inventory, project, playbook, credentials, extra variables,. Survey (host, môi trường uat, uat1, uat2, uat3) dùng để cho người dùng chọn deploy môi trường nào. Cần có các bước trên mới làm được bước này
|  | Tạo Team nếu chưa có | SA (hiện tại UAT anh Trực, PRD là anh Tuấn) |  | CD On-Prem |  | Truy cập Access Management/Team để tạo team tương ứng với Agile Team
|  | Yêu cầu Dev Login bằng LDAP | SA (hiện tại UAT anh Trực, PRD là anh Tuấn) |  | CD On-Prem |  | Nếu Dev chưa login thì yêu cầu, login rồi thì không cần.
|  | Add user vô Team | SA (hiện tại UAT anh Trực, PRD là anh Tuấn) |  | CD On-Prem
|  | Add Role trong Team (Cấp quyền Team vô Playbook) | SA (hiện tại UAT anh Trực, PRD là anh Tuấn) |  | CD On-Prem
|  | Anh Trực không nhớ có chắc là đã đủ bước chưa | SA (hiện tại UAT anh Trực, PRD là anh Tuấn) |  | CD On-Prem
- | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Note on E3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dockerfile-openshift: ENV SPRING_CONFIG_LOCATION="/home/appconfig/" ENV SPRING_LOGGING_CONFIG="${SPRING_CONFIG_LOCATION}logback.xml" https://git.dai-ichi-life.com.vn/dlvn/d-connect-system/d-connect-backend/-/blob/main/Dockerfile-openshift?ref_type=heads Helm Chart (configmap) application.properties: ¦- Helm Chart (config secret) sensitiveData: https://git.dai-ichi-life.com.vn/gitops/uat/helm-chart-d-connect-system-uat/-/blob/main/d-connect-backend/values.uat.yaml?ref_type=heads Dockerfile-openshift: ENV SPRING_CONFIG_LOCATION="/home/appconfig/" ENV SPRING_LOGGING_CONFIG="${SPRING_CONFIG_LOCATION}logback.xml" https://git.dai-ichi-life.com.vn/dlvn/d-connect-system/d-connect-backend/-/blob/main/Dockerfile-openshift?ref_type=heads Helm Chart (configmap) application.properties: ¦- Helm Chart (config secret) sensitiveData: https://git.dai-ichi-life.com.vn/gitops/uat/helm-chart-d-connect-system-uat/-/blob/main/d-connect-backend/values.uat.yaml?ref_type=heads
Note on E4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Dockerfile-openshift: ENV SPRING_CONFIG_LOCATION="/home/appconfig/" ENV SPRING_LOGGING_CONFIG="${SPRING_CONFIG_LOCATION}logback.xml" https://git.dai-ichi-life.com.vn/dlvn/d-connect-system/d-connect-backend/-/blob/main/Dockerfile-openshift?ref_type=heads Helm Chart (configmap) application.properties: ¦- Helm Chart (config secret) sensitiveData: https://git.dai-ichi-life.com.vn/gitops/uat/helm-chart-d-connect-system-uat/-/blob/main/d-connect-backend/values.uat.yaml?ref_type=heads
Note on E10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: HelmChart: Logback.xml !
Note on F16: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Đối với On-Prem thì không cần tạo project mới mà dùng chung project “artifact-releases”, phân quyền 1 lần duy nhất và đã làm rồi. User này trong Git Global Variables Trong file base.gitlab-ci.yml sẽ có đoạn docker login sử dụng biến username và password để login (cụ thể tên biến xem lại trong file base.gitlab-ci.yml (HARBOR_HOST, HARBOR_USERNAME, HARBOR_PASSWORD)
Note on B19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: App config # biến môi trường # file config theo từng môi trường
Note on F19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: CI Node,js thì bước này phải nằm trên CD On-Prem thì bước này nằm ở đây đúng

## CI.CD OnPrem Steps (hidden)
No. | Task | PIC | Is Required | Estimate | Comment
1 | Lấy danh sách nhóm ứng dụng và kèm với tài liệu cài đặt/vận hành (cài đặt ban đầu và mỗi khi promote/golive) | SA, DEV |  |  | - SA: setup server theo tài liệu này (nếu chưa có)
2 | Lấy danh sách file config của các ứng dụng (file name, location) | DEV
3 | Đưa file config ra ngoài file đóng gói ứng dụng (war,…) | DEV
4 | Tạo file .sh/.bat để build/deploy ứng dụng | DEV, DevOps | Optional | 1 day | Có thể mất thời gian hơn tùy vào độ phức tạp của ứng dụng và kinh nghiệm của dev | Nếu là OpenShift thì sẽ build bằng Docker không cần bước này
5 | Cấu trúc lại gitlab repository của ứng dụng (vd: tách BE, FE riêng từng project/repo) | DEV, DevOps |  |  | Sử dụng GitLab import/export project
6 | Tạo các file manifest (yaml) để chạy trên Ansible | DevOps |  | 1 day |  | Nếu là OpenShift thì không dùng Ansible (playbook), mà sẽ dùng ArgoCD, ArgoCD sẽ dùng Helm để chạy
7 | Tạo file .gitlab-ci.yml để chạy pipeline. | DevOps |  | 1-2 days
Cấu hình Gitlab CI:
+ Settings -> CICD -> Variables.
+ Settings -> CICD -> Runners.
8 | Hoàn thiện tích hợp full luồng CICD với GitlabCI và Ansible | DevOps |  | 1 day
Note on D5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Không dùng file .bat thì viết command line

## Truc Replatform Steps (hidden)
No. | Task | PIC | Estimate | Comment
1 | Lấy danh sách nhóm ứng dụng và kèm với tài liệu cài đặt/vận hành (cài đặt ban đầu và mỗi khi promote/golive) | SA, DEV
2 | Lấy danh sách file config của các ứng dụng (file name, location) | DEV
3 | Đưa file config ra ngoài file đóng gói ứng dụng (war,…) | DEV
4 | Liệt kê các config đường dẫn folder: | DEV
+ Lưu config ở đâu?
+ Có đọc/ghi file?
5 | Tách, quản lý cron job/ scheduler ra chạy độc lập | DEV
6 | Chuyển đổi thành containerized app (run with Dockerfile): | DevOps | 2-3 days
+ Tạo/search base image.
+ Mount thư mục share (qmulo,...), config, log.
+ File .dockerignore.
7 | Cấu trúc lại gitlab repository của ứng dụng (vd: tách BE, FE riêng từng project/repo) | DEV, DevOps
8 | Chuyển ghi log ra file thành log console nếu chạy trên k8s (OpenShift) | DEV
9 | Tạo project gitops (dùng helm chart): đưa app config vào ConfigMap, Secret; mount folder report to PV | DevOps | 2 days
10 | Tạo file .gitlab-ci.yml để chạy pipeline.Cấu hình Gitlab CI: | DevOps | 1-2 days
+ Settings -> CICD -> Variables.
+ Settings -> CICD -> Runners.
11 | Hoàn thiện tích hợp full luồng CICD với GitlabCI, ArgoCD và OpenShift | DevOps | 1 day

## Note
Lí do CI làm sau là vì có thể build tay, và sử dụng Deploy tự động
Dockerfile | Chỉ build artifact cho On-Prem
Dockerfile-openshift | Để build image cho OpenShift, nội dung file tương tự Dockerfile, chỉ thêm 1 phần Runtime stage
Config ứng dụng khác với Config đường dẫn folder. Conffig đường dẫn folder phục vụ cho việc đọc/ghi file (pdf, excel template, ...)
PV, PVC
Tất cả thứ liên quan tới Deploy (config, …) trong HELM Chart hết
Config khi Deploy OnPrem sẽ nằm trong ManagementConfig (riêng Nodejs thì vẫn trong đây nhưng phục vụ thêm cả OpenShift), OpenShift sẽ là HelmChart
Trường hợp 1 ứng dụng chưa có CI/CD, nhưng được Replatform thì trong dự án Replatform này sẽ thực hiện luôn CI/CD nhưng trực tiếp trên OpenShift?
Replatform tức là chuyển đổi CD On-Prem lên CD OpenShift
Ví dụ D-Medic không làm CI/CD nhưng Deploy lên OpenShift luôn
Key Replatforming Considerations:
● Filesystem & Storage
Key Replatforming Considerations:
● Filesystem & Storage
Identify direct filesystem usage and determine the need for persistent storage mapping (PVC).
● File Handling via API
Assess file upload/download flows to decide between temporary storage or persistent/object storage.
● Shared Storage Across Deployments
Identify use cases requiring shared mount points across multiple Deployments (e.g. sitemap generation) and define appropriate storage access modes (e.g. RWX).
● Scheduled Jobs
Review scheduled tasks and prefer Kubernetes CronJobs over long-running single-pod Deployments.
● OS-Dependent Paths
Eliminate Windows-specific paths and ensure Linux/container-compatible path handling.
● Configuration Management
Externalize and standardize application configuration using ConfigMaps, Secrets, and environment variables.
● Outbound Connectivity
Identify required outbound connections (ports, protocols, destinations) to support egress and network policies.
--------------------------------------------------------------------------------------------------------------------------------------
CI pipeline:
- Dockerfile for build
- Images build: always from catalog.redhat.com and follow container is a base platform standard guide
- Images runtime: always from catalog.redhat.com and follow container is a base platform standard guide
CD pipeline:
- OpenShift structure
- HelmChart
- Secrets
- ConfigMaps
- Deployments
- Routes/Services
on prem | build - create artifact - copy - tar (zip) - push vào harbor
build - openshift
do react nạp config lúc build, nên phải copy config từ repo ManagementConfig và ghi đè vô source code để chuẩn bị .env và index.html (optional) - build
riêng react thì luôn build 2 môi trường UAT và PRD - lí do là vì chỉ trigger build 1 lần tại thời điểm UAT (merge dev -> to uat) do đó phải chuẩn bị 2 artifacts: UAT và PRD ngay tại thời điểm này.
các loại khác thì đọc config trong lúc runtime, không phải nạp lúc build như react.
Note on A5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1. PV – Persistent Volume Persistent Volume (PV) là: Một tài nguyên lưu trữ (storage resource) ở cấp cluster Được admin hoặc hệ thống tự động (StorageClass) tạo ra Đại diện cho ổ lưu trữ thực (NFS, iSCSI, AWS EBS, GCE PD, Azure Disk, Ceph, v.v.) 👉 Hiểu đơn giản: PV = “ổ cứng” đã được cấp sẵn trong cluster Đặc điểm chính: Độc lập với Pod (Pod bị xóa thì dữ liệu vẫn còn) Có các thuộc tính như: capacity (dung lượng) accessModes (ReadWriteOnce, ReadOnlyMany, ReadWriteMany) storageClass reclaimPolicy (Retain / Delete / Recycle) 2. PVC – Persistent Volume Claim Persistent Volume Claim (PVC) là: Một yêu cầu sử dụng storage do developer / application khai báo Không quan tâm storage nằm ở đâu, chỉ quan tâm cần gì 👉 Hiểu đơn giản: PVC = “đơn xin cấp ổ cứng” PVC mô tả: Cần bao nhiêu dung lượng (ví dụ 10Gi) Cần access mode nào Cần StorageClass nào Kubernetes sẽ: Tìm một PV phù hợp để gán cho PVC hoặc Tự động tạo PV nếu dùng StorageClass (dynamic provisioning)

## Sheet1
# | Item | PIC
1 | Cách truyền config (env var / file mount) | Dev
2 | Cách quản lý secret (lưu ở đâu; cách inject) -> cần hướng đến đặt ngoài source code, không hardcode | System Admin
3 | Cơ chế logging? nếu là file thì path/rotation gì? log console ? | Dev
4 | Có Cron/Scheduler ko? tách job riêng hay chung source ? có disable theo env? | Dev
5 | Mount folder share (đường dẫn, quyền RW/RO, user/group) | System Admin
| Danh sách app + tài liệu/cách cài đặt/vận hành (install + promote/golive) | System Admin
# | Task | PIC
1 | Danh sách app + tài liệu cài đặt/vận hành (install + promote/golive) | System Admin
2 | Danh sách file server config (tên + vị trí) | System Admin
3 | Danh sách file application config (tên + vị trí) | Dev
4 | Danh sách folder share/local & permission | Dev + System Admin
5 | Cách tổ chức source code | Dev
6 | Cách build application từ source code | Dev
⭐Focus đợt này: Container + CI/CD On-Prem
# | Task | PIC
1 | Tách config khỏi war/package (đọc từ env/file mount) | Dev
2 | Tách cron/scheduler chạy độc lập (hoặc disable theo env) | Dev
3 | Đổi log file → log console (mặc định) | Dev
1 | Tạo Dockerfile + base image + .dockerignore + mount config/log/share + chạy thử | System Architecture
2 | Tạo .gitlab-ci.yml + cấu hình Runner/Variables | System Architecture
3 | Sửa base pipeline nếu không đáp ứng | System Architecture
4 | Cấu hình Harbor integration (admin) | System Admin
5 | Cấu hình Ansible (admin) | System Admin
# | Task | PIC
1 | Danh sách app + tài liệu cài đặt/vận hành (install + promote/golive) | System Admin
2 | Danh sách file server config (tên + vị trí) | System Admin
3 | Danh sách file application config (tên + vị trí) | Dev
4 | Danh sách folder share/local & permission | Dev + System Admin
5 | Cách tổ chức source code | Dev
6 | Cách build application từ source code | Dev
7 | Tách config khỏi war/package (đọc từ env/file mount) | Dev
8 | Tạo Dockerfile + base image + .dockerignore + mount config/log/share + chạy thử | System Architecture
9 | Tạo .gitlab-ci.yml + cấu hình Runner/Variables | System Architecture
10 | Sửa base pipeline nếu không đáp ứng | System Architecture
11 | Cấu hình Harbor integration (admin) | System Admin
12 | Cấu hình Ansible (admin) | System Admin

## CI
Framework | Steps | Ghi chú | Example
ACE | Copy files: .gitlab-ci.yml, Dockerfile, FlowSettings.override --> Replace name bên trong 2 file Dockerfile, FlowSettings.override |  | https://git.dai-ichi-life.com.vn/dlvn/microservices/distribution/servicing/customer-servicing/system-availability-service/-/tree/feature/sr20537-send-notifi-system-maintenance?ref_type=heads
Spring Boot | Tham khảo từ những cái project đã làm, kết hợp thêm official document Copy files: .gitlab-ci.yml, Dockerfile, Dockerfile-openshift - Dockerfile: build artifacts chạy on-prem - Dockerfile-openshift: bao gồm bước build của Dockerfile trên và bao gồm bước runtime | Thường có nhu cầu chạy song song on-prem và cloud (đối với những project Replatform). Có kết hợp F5 để config load balancing cho 2 môi trường On-prem và OpenShift, trường hợp Cloud lỗi thì config đưa về On-prem thôi để đảm bảo tính ổn định. | https://git.dai-ichi-life.com.vn/dlvn/d-connect-system/d-connect-backend
React - NextJS | Copy files: .gitlab-ci.yml, Dockerfile, Dockerfile-openshift, .dockerignore |  | https://git.dai-ichi-life.com.vn/dlvn/d-connect-system/d-connect-edoctor
ReactJS | Copy files: .gitlab-ci.yml, Dockerfile, Dockerfile-openshift, .dockerignore |  | https://git.dai-ichi-life.com.vn/dlvn/d-success-system/d-success-frontend
.NET | Copy files: .gitlab-ci.yml, Dockerfile, Dockerfile-openshift, .dockerignore |  | https://git.dai-ichi-life.com.vn/dlvn/insight-system/insight-identity-service